## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | Moscow | Dependency | Assignee | Status
S1 | S1 | US-01 | Understand the basics of the backtest.py framework so that backtesting logic can be implemented correctly. | MUST HAVE | No dependency | Nikhilesh | 3-COMPLETED
S1 | S1 | US-02 | Explore available backtesting frameworks so that the most suitable one can be chosen for the project. | SHOULD HAVE | No dependency | Nikhilesh | 3-COMPLETED
S1 | S1 | US-03 | Study the architecture of backtest.py so that trading strategies can be structured properly. | MUST HAVE | US-01 | Nikhilesh | 3-COMPLETED
S2 | S2 | US-04 | Import historical stock data using yfinance so that it can be used for strategy testing. | MUST HAVE | US-03 | Nikhilesh | 3-COMPLETED
S2 | S2 | US-05 | Clean and preprocess historical market data so that it is suitable for backtesting. | MUST HAVE | US-04 | Nikhilesh | 3-COMPLETED
S3 | S3 | US-06 | Define a trading strategy class in backtest.py so that trades can be executed programmatically. | MUST HAVE | US-03 | Nikhilesh | 3-COMPLETED
S3 | S3 | US-07 | Generate buy and sell signals based on indicators so that the strategy can make trading decisions. | MUST HAVE | US-06 | Nikhilesh | 3-COMPLETED
S4 | S4 | US-08 | Execute backtests using historical data so that strategy performance can be evaluated. | MUST HAVE | US-05, US-07 | Nikhilesh | 3-COMPLETED
S4 | S4 | US-09 | Analyze trade logs generated during backtesting so that execution accuracy can be verified. | SHOULD HAVE | US-08 | Nikhilesh | 3-COMPLETED
S5 | S5 | US-10 | Integrate machine-learning-based signals into the strategy so that advanced trading decisions can be tested. | COULD HAVE | US-08 | Nikhilesh | 3-COMPLETED
S5 | S5 | US-11 | Calculate performance metrics such as returns and drawdown so that strategy effectiveness can be measured. | MUST HAVE | US-08 | Nikhilesh | 3-COMPLETED
S6 | S6 | US-12 | Visualize backtesting results using plots so that performance trends are easy to understand. | SHOULD HAVE | US-11 | Nikhilesh | 3-COMPLETED
S6 | S6 | US-13 | Compare multiple strategies so that the best-performing strategy can be identified. | SHOULD HAVE | US-11 | Nikhilesh | 3-COMPLETED
S7 | S7 | US-14 | Optimize strategy parameters so that overall performance can be improved. | COULD HAVE | US-13 | Nikhilesh | 3-COMPLETED
S7 | S7 | US-15 | Backtest optimized strategies so that improvements can be validated. | MUST HAVE | US-14 | Nikhilesh | 3-COMPLETED
S8 | S8 | US-16 | Export backtesting results to CSV format so that results can be reused externally. | SHOULD HAVE | US-11 | Nikhilesh | 3-COMPLETED
S8 | S8 | US-17 | Export backtesting results to JSON format so that systems can consume them programmatically. | SHOULD HAVE | US-11 | Nikhilesh | 3-COMPLETED
S8 | S8 | US-18 | Document the complete backtesting workflow so that future users can understand the process. | SHOULD HAVE | US-15 | Nikhilesh | 3-COMPLETED
S8 | S8 | US-19 | Validate backtesting results against expected outcomes so that correctness is ensured. | MUST HAVE | US-15 | Nikhilesh | 3-COMPLETED
S8 | S8 | US-20 | Finalize and review the complete backtesting system so that it is ready for submission. | MUST HAVE | US-19 | Nikhilesh | 3-COMPLETED

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 143 | 66 | 53 | 21 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T1.1 | Study backtest.py basics | Day 1 | Day 2 | Nikhilesh | Learning | Done | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T1.2 | Research backtesting frameworks | Day 2 | Day 3 | Nikhilesh | Research | Done | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T1.3 | Understand backtest.py architecture | Day 3 | Day 5 | Nikhilesh | Analysis | Done | 10 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-04 | T2.1 | Import stock data using yfinance | Day 1 | Day 2 | Nikhilesh | Development | Done | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T2.2 | Clean & preprocess data | Day 2 | Day 5 | Nikhilesh | Development | Done | 8 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-06 | T3.1 | Define strategy class | Day 1 | Day 3 | Nikhilesh | Development | Done | 12 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T3.2 | Implement buy/sell signals | Day 3 | Day 5 | Nikhilesh | Development | Done | 9 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-08 | T4.1 | Execute backtests | Day 1 | Day 4 | Nikhilesh | Development | Done | 8 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T4.2 | Analyze trade logs | Day 4 | Day 5 | Nikhilesh | Analysis | Done | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 5 BACKLOG
US-10 | T5.1 | Integrate ML-based signals | Day 1 | Day 4 | Nikhilesh | Development | Done | 11 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T5.2 | Calculate performance metrics | Day 3 | Day 5 | Nikhilesh | Development | Done | 8 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 6 BACKLOG
US-12 | T6.1 | Plot performance graphs | Day 1 | Day 3 | Nikhilesh | Visualization | Done | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T6.2 | Compare multiple strategies | Day 3 | Day 5 | Nikhilesh | Analysis | Done | 8 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 7 BACKLOG
US-14 | T7.1 | Optimize strategy parameters | Day 1 | Day 4 | Nikhilesh | Optimization | Done | 9 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T7.2 | Backtest optimized strategy | Day 4 | Day 5 | Nikhilesh | Testing | Done | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 8 BACKLOG
US-16 | T8.1 | Export results to CSV | Day 1 | Day 2 | Nikhilesh | Development | Done | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T8.2 | Export results to JSON | Day 2 | Day 3 | Nikhilesh | Development | Done | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T8.3 | Document workflow | Day 3 | Day 4 | Nikhilesh | Documentation | Done | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | T8.4 | Validate results | Day 4 | Day 5 | Nikhilesh | Testing | Done | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-20 | T8.5 | Final review , submission , PPT , Demo Video | Day 5 | Day 7 | Nikhilesh | Review | Done | 9 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Standup Meeting
Sprint | Day (Date) | Impediments | Action Taken
Sprint 1 | 26-11-2025 | Initial learning curve with backtesting concepts | Team discussion and reference material review
Sprint 1 | 28-11-2025 | Difficulty understanding framework components | Studied documentation and clarified during group review
Sprint 1 | 2025-01-12 | No major impediments | Continued planned learning activities
Sprint 2 | 2025-03-12 | Delay in accessing historical stock data | Adjusted data source settings
Sprint 2 | 2025-05-12 | Data inconsistencies found | Cleaned and filtered dataset
Sprint 2 | 2025-08-12 | No major impediments | Proceeded with preprocessing tasks
Sprint 3 | 2025-10-12 | Understanding strategy class structure | Reviewed examples and team discussion
Sprint 3 | 2025-12-12 | Signal logic required refinement | Iterative testing and validation
Sprint 3 | 15-12-2025 | No major impediments | Continued implementation
Sprint 4 | 17-12-2025 | Designing alert trigger conditions | Defined alert rules and thresholds through discussion
Sprint 4 | 19-12-2025 | Email notification configuration issues | Verified SMTP settings and tested sample alerts
Sprint 4 | 22-12-2025 | No major impediments | Continued alerts module integration
Sprint 5 | 24-12-2025 | Learning curve for advanced signals | Reviewed references and examples
Sprint 5 | 26-12-2025 | Integration complexity | Incremental implementation
Sprint 5 | 29-12-2025 | No major impediments | Proceeded with metric calculations
Sprint 6 | 31-12-2025 | Scheduling alert monitoring intervals | Implemented time-based alert checks
Sprint 6 | 2026-02-01 | Alert duplication during testing | Added validation to avoid repeated notifications
Sprint 6 | 2026-05-01 | No major impediments | Alerts module stabilized and verified
Sprint 7 | 2026-07-01 | Parameter optimization took longer | Reduced parameter combinations
Sprint 7 | 2026-09-01 | Performance variation observed | Re-ran backtests for validation
Sprint 7 | 2026-12-01 | No major impediments | Finalized optimized results
Sprint 8 | 14-01-2026 | Export format alignment issues | Adjusted output structure
Sprint 8 | 20-01-2026 | Final review still in progress | Identified gaps for completion
Sprint 8 | 28-01-2026 | Project closure activities pending | Completed PPT, demo video, and finalized documentation

## Retrospection
SL # | Sprint # | Start Date | End Date | Team Name | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 26-11-2025 | 2025-02-12 | Backtesting & Alerts | Spend more time understanding fundamentals before implementation | Rushing into coding without clarity | Team discussions and reference reading | Allocated more time for learning and clarification in next sprint
2 | Sprint 2 | 2025-03-12 | 2025-09-12 | Backtesting & Alerts | Early data validation | Ignoring minor data issues initially | Collaborative problem-solving | Added data checks before preprocessing
3 | Sprint 3 | 2025-10-12 | 16-12-2025 | Backtesting & Alerts | Break strategy logic into smaller tasks | Working on complex logic in one go | Incremental implementation | Task breakdown improved in planning
4 | Sprint 4 | 17-12-2025 | 23-12-2025 | Backtesting & Alerts | Regular review of backtest outputs | Delaying validation until end | Reviewing results with team | Added mid-sprint validation step
5 | Sprint 5 | 24-12-2025 | 30-12-2025 | Backtesting & Alerts | Designing alert conditions and trigger rules early | Overloading sprint with unrelated features | Step-by-step enhancement | Defined alert criteria and basic trigger logic
6 | Sprint 6 | 31-12-2025 | 2026-06-01 | Backtesting & Alerts | Integrating email notification workflow | Manual alert testing without logs | Visualization and analysis | Implemented alert logs and notification testing
7 | Sprint 7 | 2026-07-01 | 13-01-2026 | Backtesting & Alerts | Limit optimization parameters | Running excessive combinations | Performance validation | Reduced parameter search space
8 | Sprint 8 | 14-01-2026 | 28-01-2026 | Backtesting & Alerts Team | Final PPT preparation, demo video recording, and documentation | Leaving presentation and docs to last minute | Team collaboration | Completed PPT, demo video, final documentation, and project submission